## ToDos
Title: |  | Military Idle
General | 50% | Game Logic | 11.11% | UI | 16.67% | Graphix | 0% | Specific Tasks | 0%
Type of Game | X | Class Diagram |  | Language System | X | Search for Models |  | Animation in Buildings
UI Design/Style |  | Sequenz Diagram |  | Translations |  | Create/Modify Models |  | Create Second Building
For Which Platform | X | Save and Load System | X | Create UI Elements |  | Update Models/Rebuild |  | Create/Search for Beds
Research for Plagiats |  | Think for Patterns |  | Check All UI Texts
|  | Loading Screen/Menu |  | Animate Buttons/Text/Menu
|  | Optimize Code for later Maintenance |  | CheckForAllScreenSizes
Animation
Mathematical Operations(Offline Progression)
Create Asset for Mobile Pinch and Zoom Camera Controller

## ModelList
Models to Create: | 53.33%
Straße | X
Schranke | X
Häuser non interactable
Häuser interactable fertig stellen
Soldiers
Steg | X
Laternen
Hecke
Piermauer | X
Zäune | X
Mauer | X
Bäume | X
Panzer Gebiet
T-Kreuzung Gehweg an den Seiten | X
Jeep

## Decisions
|  |  |  | WartePlatz |  | Neue Versionen
| Choices | Reasons/Notes |  | Choices | Reasons/Notes |  | Choices | Reasons/Notes |  | Choices | Reasons/Notes
| Anzahl Trupps | a 4 man
| 3(A,A,M) |  |  | Außen | "Antreten" |  | Werkstatt | Reperatur "fremder Panzer" und dadurch Geld einnehmen
| 6(3 pro Vehicle) |  |  | Innen
|  |  |  | in Reihe | Probl zu viele Trupps
| Schlafen: | 8 |  | Innen | Türen nach hinten verschieben mehr Platz im Flur
| Küche | 4 |  | Außen | Auf Gehweg wartend
| Klo | 4
Decision: | Trupps 3*6*4 | 72 | Decision: | Außen | Auf Gehweg Wartend | Decision: |  |  | Decision:
| Schlafen | 8
Küche/Klo

## Tabelle2
UI FirstOpen on CLick on Ship
not updated:
Slider
Kosten
Bonus bei Upgrade
Bonus Current